## READ ME
Instructions
Important considerations
You will be asked to identify the most critical outcomes that must be sustained, the services and input provisioning that must continue beyond the life of the activity in order to sustain each outcome, and which actor is expected to provide these critical services and inputs. Some considerations:
1. Findings from many DFSA and DFAP midterm evaluations highlight that on a large scale, volunteers are not motivated to continue to provide services after the end of an activity. When using volunteers as the main service provider, carefully consider what incentives there will be for them to continue the service provision in the absense of the RFSA support. Is community engagement enough? Is proper supportive supervision in place? What alternatives exist to promote sustained service delivery?
2. Findings from many DFSA and DFAP midterm evaluations highlight that reliance on public sector extension services that are not likely to be sustainable often undermines sustainable outcomes. If promoting the public sector as the service provider, carefully consider how quality and accountability will be assured? What alternatives exist to promote sustained and quality service or input provision?
**Note: English instructions for the other tabs of this workbook are still available, but the rows have been hidden. If you would like to review the guidance in English, please unhide the rows preceeding the French instructions.

## Sustainability Planning
It is not necessary to capture the information in this format so please do not hesitate to adapt the template to align with your team's preferences. The most important thing is to ensure that the team explores each question in depth.
Table 1: Overview of outcomes that must be sustained
TOC Outcome # | Which key outcomes in your TOC must be sustained? | Which services and input provisioning must continue beyond the life of the activity in order to sustain this outcome (e.g., agricultural extension services, health services, WASH services, business development services, skill-building services, financial services, etc.)? Transfer content to Table 2, Column A. | Which behavioral changes are critical to sustaining the key outcomes? Please list for each outcome. Transfer content to Table 3, Column A. | Optional: What, if anything, changed from your original proposal, based on learnings?
Example 1.1 | SP 1.1.2 HH members increased access to safe and nutritious food according to their nutritional needs | service 1 | Behavior 1
|  | input provision 1 | Behavior 2
service 2
Table 2: Sustainability plan for services and input provisioning | [8 empty] | Planning for post-award continuation of services and inputs ¦ Planification pour la continuation des services et des intrants post-attribution
| Who will provide services and inputs | Strategy roll out timeline | Public sector strategy For all cells highlighted yellow in column B | Market-based / fee-based service provision Please answer the following for all cells highlighted in orange in Column A. |  |  | Change timeline | Monitoring | Post-award Motivation | Post-award Resources | Post-award Capacity Strengthening
Please list all services and input provisioning that must continue beyond the LOA from column C in Table 1. Please highlight in orange any market-based service provision. | How will each crucial service or input be provided after the end of the RFSA? List each responsible entity. Please highlight cells in yellow that list the public sector as having a role in service or input provision. What, if anything, changed from your original proposal based on learnings? | Examples include, when will the RFSA train the local service providers (LSP)? When will participants be linked to local service providers? When will local service providers be linked to resources and ongoing sources for capacity strengthening necessary during the life of the award? What, if anything, changed from your original proposal, based on learnings? | How will the accountability and quality of public service providers and local government be improved? What, if anything, changed from your original proposal, based on learnings? | If a market-based service/input provisioning system is envisioned, what business model will be used for each type of service provider? What, if anything, changed from your original proposal, based on learnings? | Are you prepared to share the economic analysis of the business model with BHA? If the economic analysis hasn’t happened yet when will it be done? | Describe the strategy the RFSA will employ to improve participant motivation to pay for services. What, if anything, changed from your original proposal, based on learnings? | At what point in the RFSA cycle do you expect to see change occur (e.g., positive shifts in motivation, formal handover to public or private providers for service delivery or input provision)? What, if anything, changed from your original proposal, based on learnings? | How will you monitor that change is occurring? How will you monitor that handover/ phaseover is on track? How will the performance of the service/input providers be monitored after handover? How will you monitor the challenges LSPs face? | What is the motivation of the service and input providers to continue to provide services after the end of the award? How will motivation of the services providers be enhanced and improved? What, if anything, changed from your original proposal, based on learnings? | What is the RFSA's plan to help service and input providers to identify reliable access to the resources necessary for post-award provision of services and inputs ? What, if anything, changed from your original proposal, based on learnings? | What is RFSA's plan to help the potential service and input providers access capacity strengthening support after the end of the Activity? What, if anything, changed from your original proposal, based on learnings?
sample: agricultural extension services
Table 3: Plan for sustained participant adoption
Behaviors/Practices to Continue | Resources | Capacity | Motivation
Please list all behavior/ adoption of practices that must continue beyond the LOA from column D in Table 1. | Resources: How will individuals, households, and communities access necessary resources to sustain the adoption of listed behaviors / practices? | Capacity: How will individuals, households, and communities access services that strengthen their capacity to a) implement recommended practices and b) manage resources necessary to sustain adoption? | Motivation: What will motivate participants to continue new behaviors and practices after the end of the RFSA? How will motivation of the participants be enhanced and improved?
Behaviour 1
Behaviour 2

## Questions for BHA
QUESTION | Portion of the sustainability planning guidance that your question relates to. E.g. Market-based service provision or monitoring | Name